## Daily To Do List
ISSUE ID | TASK DESCRIPTION |  | TIMELINE | [8 empty] | CATEGORY | ACTUAL | STATUS | REVIEW |  | PENDING ACTIONS | DOCUMENT | MEMO
|  | Member | START DATE | END DATE | # of DAYS | START DAY | DATE DUE | TIME DUE | HOLIDAY | # of DAYS DUE | PERCENT |  |  |  | REVIEWER | STATUS
Create project skeleton VueJS | Header, body, footer | HongNT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | VUEJS |  | IN PROGRESS
| Router | [10 empty] | VUEJS |  | IN PROGRESS
| Store | [10 empty] | VUEJS |  | IN PROGRESS
| VueI18n | [10 empty] | VUEJS |  | IN PROGRESS
Create project skeleton Spring boot | Project sample | QueBX | 2020-08-20 | 2020-08-21 |  | 2020-08-20 | 2020-08-21 | 12h |  |  |  | Spring |  | IN PROGRESS
| Logback | QueBX | [9 empty] | Spring |  | IN PROGRESS
| Migration | QueBX | [9 empty] | Spring |  | IN PROGRESS
| HandleException | QueBX | [9 empty] | Spring |  | IN PROGRESS
Create file sql | All file | LinhNV | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | SQL |  | IN PROGRESS
Create file document đăng nhập | Login | DatBT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | API |  | IN PROGRESS
| Logout | DatBT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | API |  | IN PROGRESS
| ChangePassword by password | DatBT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | API |  | IN PROGRESS
| Send mail forgot password | DatBT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | API |  | IN PROGRESS
| ChangePassword by code email | DatBT | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 | 2020-08-21 | 12h |  |  |  | API |  | IN PROGRESS
[15 empty] | 0 | 0 | 0

## Issue
STT | API/SCREEN | STATUS | MEMO

## Sheet1
ISSUE ID | TASK DESCRIPTION |  | TIMELINE | [8 empty] | ACTUAL
|  | Member | START DATE | END DATE | # of DAYS | START DAY | DATE DUE | TIME DUE | HOLIDAY | # of DAYS DUE | PERCENT