## Common
ISSUE ID | TASK DESCRIPTION |  |  | TIMELINE | [9 empty] | CATEGORY | ACTUAL | STATUS | REVIEW |  | PENDING ACTIONS | DOCUMENT | MEMO
|  | Member | Support task | START DATE | END DATE | # of DAYS | START DAY | TIME DUE | DATE DUE | TIME DUE | HOLIDAY | # of DAYS DUE | PERCENT |  |  |  | REVIEWER | STATUS
Create project skeleton VueJS | Header, body, footer | HongNT | HuognMV | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 |  | 2020-08-21 | 12h |  |  |  | VUEJS |  | DONE
| Router | HongNT | HuognMV | [10 empty] | VUEJS |  | DONE
| Store | HongNT | HuognMV | [10 empty] | VUEJS |  | DONE
| VueI18n | HongNT | [11 empty] | VUEJS |  | DONE
Create project skeleton Spring boot | Project sample | QueBX |  | 2020-08-20 | 2020-08-21 |  | 2020-08-20 |  | 2020-08-21 | 12h |  |  |  | Spring |  | DONE
| Logback | QueBX | [11 empty] | Spring |  | DONE
| Migration | QueBX | [11 empty] | Spring |  | DONE
| HandleException | QueBX |  | 31/8/2020 | 3/0/2020 | [8 empty] | Spring |  | DONE
Create file sql | All file | HuognMV | HuognMV | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 |  | 2020-08-21 | 12h |  |  |  | SQL |  | DONE
Create structures server |  | HuognMV |  | 2020-08-20 | 2020-08-21 | 2 | 2020-08-20 |  | 2020-08-21 | 12h |  |  |  | Folder |  | DONE
[17 empty] | 0 | 0 | 0

## API
ISSUE ID | TASK DESCRIPTION |  |  | TIMELINE | [9 empty] | CATEGORY | ACTUAL | STATUS | REVIEW |  | PENDING ACTIONS | DOCUMENT | MEMO
|  | Member | Support task | START DATE | END DATE | # of DAYS | START DAY | TIME DUE | DATE DUE | TIME DUE | HOLIDAY | # of DAYS DUE | PERCENT |  |  |  | REVIEWER | STATUS
/cmn/countryList | Create basic design | QueBX |  | 2020-04-09 | 2020-04-09 | [10 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/login | Create basic design | HongNT |  | 2020-08-31 | 2020-08-31 |  | 2020-08-31 |  | 2020-08-31 | [6 empty] | DONE
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/logOut | Create basic design | HongNT |  | 2020-01-09 | 2020-01-09 |  | 2020-01-09 |  | 2020-01-09 | [6 empty] | DONE
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/register | Create basic design | HongNT | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/forgotPassword | Create basic design | HongNT | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/changePassword | Create basic design | HongNT |  | 2020-01-09 | 2020-01-09 |  | 2020-01-09 |  | 2020-01-09 | [6 empty] | DONE
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/changePassByEmail | Create basic design | HongNT | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/userList | Create basic design | QueBX | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/editUser | Create basic design | QueBX | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/addUser | Create basic design | QueBX | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/deleteUser | Create basic design | QueBX | [13 empty] | NOT YET
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/import/userList | Create basic design | HongNT |  | 2020-03-09 | 2020-03-09 |  | 2020-03-09 |  | 2020-03-09 | [6 empty] | INPROGRESS
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET
/admin/import/userBase64 | Create basic design | QueBX |  | 2020-03-09 | 2020-03-09 |  | 2020-03-09 |  | 2020-03-09 | [6 empty] | INPROGRESS
| Coding API | [14 empty] | NOT YET
| Coding Client | [14 empty] | NOT YET
| Mapper API vs client | [14 empty] | NOT YET

## Issue
STT | API/SCREEN | STATUS | MEMO

## Sheet1
ISSUE ID | TASK DESCRIPTION |  | TIMELINE | [8 empty] | ACTUAL
|  | Member | START DATE | END DATE | # of DAYS | START DAY | DATE DUE | TIME DUE | HOLIDAY | # of DAYS DUE | PERCENT