## 20200825
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Login | 0% | chua hoan thanh
2 | Register | 0% | chua hoan thanh
3 | ForgotPassword | 0% | chua hoan thanh

## 20200826
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Login | 50% | chua hoan thanh | Screen + API crud da xong Dang doc JWT
2 | Register | 50% | chua hoan thanh
3 | ForgotPassword | 50% | chua hoan thanh

## 20200828
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Login | 50% | chua hoan thanh | Screen + API crud da xong Dang doc JWT
2 | Register | 50% | chua hoan thanh
4 | List User | 20% | Chua hoan thanh | chuyen sang viet api list Country
5 | Api list country | 70% | Chua hoan thanh

## 20200831
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Login | 50% | chua hoan thanh | Screen + API crud da xong Dang doc JWT
2 | Register | 50% | chua hoan thanh
4 | List User | 100% | Hoan thanh
5 | Api list country | 70% | Chua hoan thanh

## 20200901
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Login | 50% | chua hoan thanh | Screen + API crud da xong Dang doc JWT
2 | Register | 50% | chua hoan thanh
4 | List User | 100% | Hoan thanh
5 | Api list country | 70% | Chua hoan thanh
Ngay hom nay lam thu tuc ben Nhat nen tien do Task bi cham

## 20200903
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Api list country | 100% | hoan thanh
2 | Import File create base design | 75% | Chua hoan thanh

## 20200904
STT | API/SCREEN | PERCENT | STATUS | MEMO
1 | Import File create base design | 100% | hoan thanh